## Sheet1
AgroSmart
Sr. | Points | Deadline | Priority | Fetures | Testing | Status
1 | API Creation Of All Table |  |  | crud DDL | Done | Complatted
2 | Complete Crud And Filter on crop table |  |  | perform crud and filter | Done | Compalted | Goal | Complete AgroSmart Project
3 | Complete Crud And Filter on Farm table | 2025-07-31
4 | Complete Crud And Filter on Field table | 2025-07-31
5 | Link Farm Field Crop with FieldWiseCrop table | 2025-07-31
6 | Weather CRUD and fetching from live api | 2025-07-31
7 | Implement Schdeule | 2025-08-05
8 | Implement Sensors | 2025-08-10
9 | Auto get Sensor Readings | 2025-08-15
10 | work on SmartInsights | 2025-08-25
11 | Work on login and user profile | 2025-08-30
12 | Work on Dashboard | 2025-09-05